## Weekly Report
EASM Mission – Weekly Status Report
EASM Assessment – 2LoD Cyber Risk Intelligence
| Meeting date | 2026-10-20 |  | Reporting period | 14-Oct to 20-Oct-2026
| Prev. meeting | 2026-10-13 |  | Next-week window | 21-Oct to 27-Oct-2026
Edit only the two boxed dates. Everything below fills in automatically from the other tabs.
1 | Overall Timeline
# | Week | Mission period | Day | % time elapsed | Current phase | Plan check
| Week 3 | 05-Oct-2026 → 29-Jan-2027 | 16 of 117 | 12.93% | Kick-off & Alignment | On plan
# | Phase | Phase name | Planned start | Planned end | Status | Actions completed
| P1 | Kick-off & Alignment | 2026-10-05 | 2026-10-23 | In Progress | 100%
| P2 | Assessment & Execution | 2026-10-26 | 2026-12-18 | Not Started | 0%
| P3 | Reporting & Conclusion | 2027-01-04 | 2027-01-29 | Not Started | 0%
2 | Overall Status
# | RAG | Why (one sentence)
| Amber | Kick-off completed on time, but the inventory audit is held back by the missing EASM procedure and a pending scope decision.
# | Suggested RAG | Overdue actions | Blocked actions | Open escalations | Phases behind plan | Meetings / emails this period
| Amber | 0 | 1 | 1 | 0 | Meetings: 1 ¦ Emails: 0
3 | Progress Since Last Week |  |  |  |  | 2 item(s)
# | ID | Action | Owner | Status | Focus area | Progress note
1 | ACT-001 | Kick-off meeting with CISO Office and Network Security; agree scope and data requests | Me | Completed | Governance | Scope agreed: 3 legal entities, root domains and public IP ranges
2 | ACT-002 | Reconcile EASM-discovered assets against CMDB extract | Me | In Progress | Visibility | First pass done: ~18% of discovered hosts not in CMDB
4 | Current Work |  |  |  |  | 1 item(s)
# | ID | Action | Owner | Due date | Focus area | Progress note
1 | ACT-002 | Reconcile EASM-discovered assets against CMDB extract | Me | 2026-11-06 | Visibility | First pass done: ~18% of discovered hosts not in CMDB
5 | Findings – New or Materially Changed |  |  |  |  | 1 item(s)
# | ID | Finding | Severity | Remediation status | New / Changed | Update / remediation
1 | FND-001 | ~18% of internet-facing hosts discovered by EASM are not recorded in the CMDB (mostly acquired entity B) | High | Open | New | New – root cause analysis requested from 1LoD
6 | Blockers & Dependencies |  |  |  |  | 1 item(s)
# | ID | Blocker / dependency | Waiting on | Status | Due date | Related action
1 | ACT-003 | Current version of the EASM procedure not yet shared by 1LoD | Network Security (1LoD) | Blocked | 2026-10-27 | Review EASM operating procedure and asset ownership policy
7 | Plan for Next Week |  |  |  |  | 2 item(s)
# | ID | Action | Owner | Due date | Status | Focus area
1 | ACT-002 | Reconcile EASM-discovered assets against CMDB extract | Me | 2026-11-06 | In Progress | Visibility
2 | ACT-003 | Review EASM operating procedure and asset ownership policy | Me | 2026-10-27 | Blocked | Governance
8 | Escalations & Decisions Needed |  |  |  |  | 1 item(s)
# | ID | Issue / decision required | Decision maker | Type | Needed by | Recommendation
1 | ESC-001 | Extend mission scope to the 3 acquired entities' domains and IP ranges | Mission Sponsor | Decision Needed | 2026-10-27 | Approve extension; timeline +2 weeks for phase 2
Source: Actions, Findings, Escalations, Weekly Status and Timeline tabs. Overall RAG is the analyst's judgement; 'Suggested RAG' is an indicative rule (see cell note).
Note on B20: Rule of thumb only – your judgement in Weekly Status prevails. Red: a phase behind plan or ≥3 overdue actions. Amber: any overdue or blocked action, or any open escalation. Green: otherwise.
Note on C4: Defaults to today. Overwrite with your meeting date to rebuild the report for another week.
Note on C5: Defaults to 7 days before. Overwrite if meetings are not exactly weekly.

## Weekly Status
Weekly Status
One row per weekly meeting: your overall RAG and the one-sentence reason. Builds a status history.
White = you type ¦ Grey = automatic ¦ Italic rows = examples (overwrite or delete)
Meeting Date | Overall Status (RAG) | Why (one sentence) | Other Notes | helper:wk
2026-10-20 | Amber | Kick-off completed on time, but the inventory audit is held back by the missing EASM procedure and a pending scope decision. |  | 1

## Timeline
Timeline
Mission dates, the 3 phases and coverage of methods × focus areas.
White = you type ¦ Grey = automatic ¦ Italic rows = examples (overwrite or delete)
Mission name | EASM Assessment – 2LoD Cyber Risk Intelligence
Mission start | 2026-10-05
Mission end | 2027-01-29
# | Phase | Planned Start | Planned End | Actual Start | Actual End | Status | Actions | Completed | % Complete | Plan Check | Comment
P1 | Kick-off & Alignment | 2026-10-05 | 2026-10-23 | 2026-10-05 |  | In Progress | 1 | 1 | 100% | On plan
P2 | Assessment & Execution | 2026-10-26 | 2026-12-18 |  |  | Not Started | 2 | 0 | 0% | On plan
P3 | Reporting & Conclusion | 2027-01-04 | 2027-01-29 |  |  | Not Started | 0 | 0 | 0% | On plan
Coverage – number of actions per focus area and method (cancelled excluded)
Focus Area | Document Review | Stakeholder Engagement | Inventory Audit | Completeness Validation | Total Actions | Open Findings
Visibility | 0 | 0 | 1 | 0 | 1 | 1
Governance | 1 | 1 | 0 | 0 | 2 | 0
Integration | 0 | 0 | 0 | 0 | 0 | 0
Sustainability | 0 | 0 | 0 | 0 | 0 | 0
Amber cell = no action yet for that focus area / method combination (possible coverage gap).

## Actions
Actions
Every task of the mission. Update Status, Last Updated and Progress Note before each weekly meeting.
White = you type ¦ Grey = automatic ¦ Italic rows = examples (overwrite or delete)
ID | Phase | Action / Task | Method | Focus Area | Owner | Start Date | Due Date | Status | Completed Date | Last Updated | Progress Note (latest) | Blocker / Dependency | Waiting On (who) | Plan for Next Week? | Overdue? | helper:prog | helper:curr | helper:blk | helper:next
ACT-001 | Kick-off & Alignment | Kick-off meeting with CISO Office and Network Security; agree scope and data requests | Stakeholder Engagement | Governance | Me | 2026-10-05 | 2026-10-16 | Completed | 2026-10-15 | 2026-10-15 | Scope agreed: 3 legal entities, root domains and public IP ranges |  |  | No |  | 1
ACT-002 | Assessment & Execution | Reconcile EASM-discovered assets against CMDB extract | Inventory Audit | Visibility | Me | 2026-10-14 | 2026-11-06 | In Progress |  | 2026-10-19 | First pass done: ~18% of discovered hosts not in CMDB |  |  | Yes |  | 2 | 1 |  | 1
ACT-003 | Assessment & Execution | Review EASM operating procedure and asset ownership policy | Document Review | Governance | Me | 2026-10-19 | 2026-10-27 | Blocked |  |  |  | Current version of the EASM procedure not yet shared by 1LoD | Network Security (1LoD) | Yes |  |  |  | 1 | 2
ACT-004
ACT-005
ACT-006
ACT-007
ACT-008
ACT-009
ACT-010
ACT-011
ACT-012
ACT-013
ACT-014
ACT-015
ACT-016
ACT-017
ACT-018
ACT-019
ACT-020
ACT-021
ACT-022
ACT-023
ACT-024
ACT-025
ACT-026
ACT-027
ACT-028
ACT-029
ACT-030
ACT-031
ACT-032
ACT-033
ACT-034
ACT-035
ACT-036
ACT-037
ACT-038
ACT-039
ACT-040
ACT-041
ACT-042
ACT-043
ACT-044
ACT-045
ACT-046
ACT-047
ACT-048
ACT-049
ACT-050
ACT-051
ACT-052
ACT-053
ACT-054
ACT-055
ACT-056
ACT-057
ACT-058
ACT-059
ACT-060
ACT-061
ACT-062
ACT-063
ACT-064
ACT-065
ACT-066
ACT-067
ACT-068
ACT-069
ACT-070
ACT-071
ACT-072
ACT-073
ACT-074
ACT-075
ACT-076
ACT-077
ACT-078
ACT-079
ACT-080
ACT-081
ACT-082
ACT-083
ACT-084
ACT-085
ACT-086
ACT-087
ACT-088
ACT-089
ACT-090
ACT-091
ACT-092
ACT-093
ACT-094
ACT-095
ACT-096
ACT-097
ACT-098
ACT-099
ACT-100
ACT-101
ACT-102
ACT-103
ACT-104
ACT-105
ACT-106
ACT-107
ACT-108
ACT-109
ACT-110
ACT-111
ACT-112
ACT-113
ACT-114
ACT-115
ACT-116
ACT-117
ACT-118
ACT-119
ACT-120
ACT-121
ACT-122
ACT-123
ACT-124
ACT-125
ACT-126
ACT-127
ACT-128
ACT-129
ACT-130
ACT-131
ACT-132
ACT-133
ACT-134
ACT-135
ACT-136
ACT-137
ACT-138
ACT-139
ACT-140
ACT-141
ACT-142
ACT-143
ACT-144
ACT-145
ACT-146
ACT-147
ACT-148
ACT-149
ACT-150
ACT-151
ACT-152
ACT-153
ACT-154
ACT-155
ACT-156
ACT-157
ACT-158
ACT-159
ACT-160
ACT-161
ACT-162
ACT-163
ACT-164
ACT-165
ACT-166
ACT-167
ACT-168
ACT-169
ACT-170
ACT-171
ACT-172
ACT-173
ACT-174
ACT-175
ACT-176
ACT-177
ACT-178
ACT-179
ACT-180
ACT-181
ACT-182
ACT-183
ACT-184
ACT-185
ACT-186
ACT-187
ACT-188
ACT-189
ACT-190
ACT-191
ACT-192
ACT-193
ACT-194
ACT-195
ACT-196
ACT-197
ACT-198
ACT-199
ACT-200
Formulas:
Overdue? = IF(OR([Action / Task]="",[Due Date]="",[Status]="Completed",[Status]="Cancelled"),"",IF([Due Date]<TODAY(),"Overdue",""))
Note on K4: Set this date whenever the action moves forward — it puts the action in 'Progress since last week'.
Note on M4: Anything preventing progress or needed from someone else. Leave blank if none.
Note on O4: Yes = show in 'Plan for next week'. Actions due within 7 days after the meeting appear automatically.

## Findings
Findings
Mission findings. 'This Period' flags new or materially changed findings for the weekly report.
White = you type ¦ Grey = automatic ¦ Italic rows = examples (overwrite or delete)
ID | Date Identified | Focus Area | Method | Finding (what & where) | Risk / Impact | Severity | Remediation Owner | Remediation Status | Target Date | Last Material Change | What Changed / Remediation Update | This Period | Overdue? | helper:rep
FND-001 | 2026-10-16 | Visibility | Inventory Audit | ~18% of internet-facing hosts discovered by EASM are not recorded in the CMDB (mostly acquired entity B) | Unmanaged assets outside patching and monitoring; incomplete ICT asset register | High | Network Security (1LoD) | Open | 2026-12-15 |  | New – root cause analysis requested from 1LoD | New |  | 1
FND-002
FND-003
FND-004
FND-005
FND-006
FND-007
FND-008
FND-009
FND-010
FND-011
FND-012
FND-013
FND-014
FND-015
FND-016
FND-017
FND-018
FND-019
FND-020
FND-021
FND-022
FND-023
FND-024
FND-025
FND-026
FND-027
FND-028
FND-029
FND-030
FND-031
FND-032
FND-033
FND-034
FND-035
FND-036
FND-037
FND-038
FND-039
FND-040
FND-041
FND-042
FND-043
FND-044
FND-045
FND-046
FND-047
FND-048
FND-049
FND-050
FND-051
FND-052
FND-053
FND-054
FND-055
FND-056
FND-057
FND-058
FND-059
FND-060
FND-061
FND-062
FND-063
FND-064
FND-065
FND-066
FND-067
FND-068
FND-069
FND-070
FND-071
FND-072
FND-073
FND-074
FND-075
FND-076
FND-077
FND-078
FND-079
FND-080
FND-081
FND-082
FND-083
FND-084
FND-085
FND-086
FND-087
FND-088
FND-089
FND-090
FND-091
FND-092
FND-093
FND-094
FND-095
FND-096
FND-097
FND-098
FND-099
FND-100
FND-101
FND-102
FND-103
FND-104
FND-105
FND-106
FND-107
FND-108
FND-109
FND-110
FND-111
FND-112
FND-113
FND-114
FND-115
FND-116
FND-117
FND-118
FND-119
FND-120
FND-121
FND-122
FND-123
FND-124
FND-125
FND-126
FND-127
FND-128
FND-129
FND-130
FND-131
FND-132
FND-133
FND-134
FND-135
FND-136
FND-137
FND-138
FND-139
FND-140
FND-141
FND-142
FND-143
FND-144
FND-145
FND-146
FND-147
FND-148
FND-149
FND-150
FND-151
FND-152
FND-153
FND-154
FND-155
FND-156
FND-157
FND-158
FND-159
FND-160
FND-161
FND-162
FND-163
FND-164
FND-165
FND-166
FND-167
FND-168
FND-169
FND-170
FND-171
FND-172
FND-173
FND-174
FND-175
FND-176
FND-177
FND-178
FND-179
FND-180
FND-181
FND-182
FND-183
FND-184
FND-185
FND-186
FND-187
FND-188
FND-189
FND-190
FND-191
FND-192
FND-193
FND-194
FND-195
FND-196
FND-197
FND-198
FND-199
FND-200
Formulas:
Overdue? = IF(OR([Finding (what & where)]="",[Target Date]="",[Remediation Status]="Remediated",[Remediation Status]="Closed",[Remediation Status]="Risk Accepted"),"",IF([Target Date]<TODAY(),"Overdue",""))
Note on K4: Date of the last material change (severity, scope, remediation status). It puts the finding back in the weekly report.

## Escalations
Escalations & Decisions
Items that need an escalation or a decision. Open items appear in the weekly report.
White = you type ¦ Grey = automatic ¦ Italic rows = examples (overwrite or delete)
ID | Date Raised | Type | Issue / Decision Required | Impact if Unresolved | Options / Recommendation | Escalate To / Decision Maker | Needed By | Status | Resolution Date | Outcome | helper:open
ESC-001 | 2026-10-19 | Decision Needed | Extend mission scope to the 3 acquired entities' domains and IP ranges | Material part of the external attack surface would stay unassessed | Approve extension; timeline +2 weeks for phase 2 | Mission Sponsor | 2026-10-27 | Open |  |  | 1
ESC-002
ESC-003
ESC-004
ESC-005
ESC-006
ESC-007
ESC-008
ESC-009
ESC-010
ESC-011
ESC-012
ESC-013
ESC-014
ESC-015
ESC-016
ESC-017
ESC-018
ESC-019
ESC-020
ESC-021
ESC-022
ESC-023
ESC-024
ESC-025
ESC-026
ESC-027
ESC-028
ESC-029
ESC-030
ESC-031
ESC-032
ESC-033
ESC-034
ESC-035
ESC-036
ESC-037
ESC-038
ESC-039
ESC-040
ESC-041
ESC-042
ESC-043
ESC-044
ESC-045
ESC-046
ESC-047
ESC-048
ESC-049
ESC-050
ESC-051
ESC-052
ESC-053
ESC-054
ESC-055
ESC-056
ESC-057
ESC-058
ESC-059
ESC-060
ESC-061
ESC-062
ESC-063
ESC-064
ESC-065
ESC-066
ESC-067
ESC-068
ESC-069
ESC-070
ESC-071
ESC-072
ESC-073
ESC-074
ESC-075
ESC-076
ESC-077
ESC-078
ESC-079
ESC-080
ESC-081
ESC-082
ESC-083
ESC-084
ESC-085
ESC-086
ESC-087
ESC-088
ESC-089
ESC-090
ESC-091
ESC-092
ESC-093
ESC-094
ESC-095
ESC-096
ESC-097
ESC-098
ESC-099
ESC-100
ESC-101
ESC-102
ESC-103
ESC-104
ESC-105
ESC-106
ESC-107
ESC-108
ESC-109
ESC-110
ESC-111
ESC-112
ESC-113
ESC-114
ESC-115
ESC-116
ESC-117
ESC-118
ESC-119
ESC-120
ESC-121
ESC-122
ESC-123
ESC-124
ESC-125
ESC-126
ESC-127
ESC-128
ESC-129
ESC-130
ESC-131
ESC-132
ESC-133
ESC-134
ESC-135
ESC-136
ESC-137
ESC-138
ESC-139
ESC-140
ESC-141
ESC-142
ESC-143
ESC-144
ESC-145
ESC-146
ESC-147
ESC-148
ESC-149
ESC-150
ESC-151
ESC-152
ESC-153
ESC-154
ESC-155
ESC-156
ESC-157
ESC-158
ESC-159
ESC-160
ESC-161
ESC-162
ESC-163
ESC-164
ESC-165
ESC-166
ESC-167
ESC-168
ESC-169
ESC-170
ESC-171
ESC-172
ESC-173
ESC-174
ESC-175
ESC-176
ESC-177
ESC-178
ESC-179
ESC-180
ESC-181
ESC-182
ESC-183
ESC-184
ESC-185
ESC-186
ESC-187
ESC-188
ESC-189
ESC-190
ESC-191
ESC-192
ESC-193
ESC-194
ESC-195
ESC-196
ESC-197
ESC-198
ESC-199
ESC-200

## Meetings & Emails
Meetings & Emails
Record of meetings, emails and calls under the mission.
White = you type ¦ Grey = automatic ¦ Italic rows = examples (overwrite or delete)
ID | Date | Type | Subject | With (people / function) | Key Points / Outcome | Actions Created (IDs) | Notes
LOG-001 | 2026-10-15 | Meeting | EASM mission kick-off | CISO Office; Network Security; Group Architecture | Scope and data requests agreed; CMDB extract to be shared by 1LoD | ACT-001; ACT-002
LOG-002
LOG-003
LOG-004
LOG-005
LOG-006
LOG-007
LOG-008
LOG-009
LOG-010
LOG-011
LOG-012
LOG-013
LOG-014
LOG-015
LOG-016
LOG-017
LOG-018
LOG-019
LOG-020
LOG-021
LOG-022
LOG-023
LOG-024
LOG-025
LOG-026
LOG-027
LOG-028
LOG-029
LOG-030
LOG-031
LOG-032
LOG-033
LOG-034
LOG-035
LOG-036
LOG-037
LOG-038
LOG-039
LOG-040
LOG-041
LOG-042
LOG-043
LOG-044
LOG-045
LOG-046
LOG-047
LOG-048
LOG-049
LOG-050
LOG-051
LOG-052
LOG-053
LOG-054
LOG-055
LOG-056
LOG-057
LOG-058
LOG-059
LOG-060
LOG-061
LOG-062
LOG-063
LOG-064
LOG-065
LOG-066
LOG-067
LOG-068
LOG-069
LOG-070
LOG-071
LOG-072
LOG-073
LOG-074
LOG-075
LOG-076
LOG-077
LOG-078
LOG-079
LOG-080
LOG-081
LOG-082
LOG-083
LOG-084
LOG-085
LOG-086
LOG-087
LOG-088
LOG-089
LOG-090
LOG-091
LOG-092
LOG-093
LOG-094
LOG-095
LOG-096
LOG-097
LOG-098
LOG-099
LOG-100
LOG-101
LOG-102
LOG-103
LOG-104
LOG-105
LOG-106
LOG-107
LOG-108
LOG-109
LOG-110
LOG-111
LOG-112
LOG-113
LOG-114
LOG-115
LOG-116
LOG-117
LOG-118
LOG-119
LOG-120
LOG-121
LOG-122
LOG-123
LOG-124
LOG-125
LOG-126
LOG-127
LOG-128
LOG-129
LOG-130
LOG-131
LOG-132
LOG-133
LOG-134
LOG-135
LOG-136
LOG-137
LOG-138
LOG-139
LOG-140
LOG-141
LOG-142
LOG-143
LOG-144
LOG-145
LOG-146
LOG-147
LOG-148
LOG-149
LOG-150
LOG-151
LOG-152
LOG-153
LOG-154
LOG-155
LOG-156
LOG-157
LOG-158
LOG-159
LOG-160
LOG-161
LOG-162
LOG-163
LOG-164
LOG-165
LOG-166
LOG-167
LOG-168
LOG-169
LOG-170
LOG-171
LOG-172
LOG-173
LOG-174
LOG-175
LOG-176
LOG-177
LOG-178
LOG-179
LOG-180
LOG-181
LOG-182
LOG-183
LOG-184
LOG-185
LOG-186
LOG-187
LOG-188
LOG-189
LOG-190
LOG-191
LOG-192
LOG-193
LOG-194
LOG-195
LOG-196
LOG-197
LOG-198
LOG-199
LOG-200

## How To Use
How To Use
WEEKLY ROUTINE (≈10 min before the meeting)
1. Actions | Update Status, Last Updated date and Progress Note for anything that moved. Fill Blocker / Waiting On where relevant. Set 'Plan for Next Week' = Yes for next week's work.
2. Findings | Add new findings. For existing ones, set 'Last Material Change' and describe the change and the remediation status.
3. Escalations | Add anything needing escalation or a decision. Set Status = Resolved once closed.
4. Weekly Status | Add one row: meeting date, overall RAG and one sentence explaining why. Check it against the 'Suggested RAG' on the report.
5. Timeline | Update phase status and actual dates when a phase starts or ends.
6. Weekly Report | Check the meeting date (defaults to today). All 8 sections fill in automatically. Print (1 page wide) or copy into email or slides.
HOW ITEMS REACH THE REPORT
Progress since last week | Actions completed, or with 'Last Updated', after the previous meeting and up to this meeting.
Current work | Actions with Status = In Progress.
Findings | Findings identified, or materially changed, in the reporting period.
Blockers & dependencies | Open actions with Status = Blocked or with a Blocker / Dependency entered.
Plan for next week | Open actions flagged 'Plan for Next Week' = Yes, or due within 7 days after the meeting.
Escalations & decisions | Escalations with Status = Open.
MISSION STRUCTURE
Phases | Kick-off & Alignment → Assessment & Execution → Reporting & Conclusion
Methods | Document Review · Stakeholder Engagement · Inventory Audit · Completeness Validation
Focus areas | Visibility · Governance · Integration · Sustainability (coverage matrix on the Timeline tab)
NOTES
Colours | Emerald = headers. White = input. Grey = automatic, do not overwrite. Green / amber / red = status.
Examples | Italic rows are examples. Overwrite or delete them before first use.
Capacity | 200 rows per log. Report shows up to 8 items per section; the section header shows the total.

## Lists
Dropdown values (edit here if needed)
Phase | Method | Focus | ActStatus | PhaseStatus | RAG | Severity | RemStatus | EscType | EscStatus | LogType | YesNo
Kick-off & Alignment | Document Review | Visibility | Not Started | Not Started | Green | Critical | Open | Escalation | Open | Meeting | Yes
Assessment & Execution | Stakeholder Engagement | Governance | In Progress | In Progress | Amber | High | In Progress | Decision Needed | Resolved | Email | No
Reporting & Conclusion | Inventory Audit | Integration | Blocked | Delayed | Red | Medium | Remediated |  |  | Call
| Completeness Validation | Sustainability | Completed | Completed |  | Low | Risk Accepted
| N/A (Project Mgmt) | Cross-cutting | Cancelled |  |  |  | Closed