## Guide
EASM Mission Tracker — Guide
Cyber Risk Intelligence (2LoD) — one workbook for meetings, communications, tasks, goals, developments and EASM findings, producing the weekly status report automatically.
WEEKLY ROUTINE (≈15 min before the meeting)
1 · During the week | Log as things happen: Meetings, Emails, Developments, EASM Findings. On Tasks keep Status, % Complete, Last Update Date and Latest Update Note current.
2 · Findings | When severity, status, exploitation, ownership or RAF view changes, set 'Last Material Change Date' and describe the change. New/changed findings flow to section 5.
3 · Goals | Copy 'Current Value' into 'Value Last Week', then enter the new Current Value and Last Updated date.
4 · Plan & dependencies | On Tasks set 'Planned for Next Week? = Yes' and fill 'Dependency On' / 'Needed By' for anything waiting on others. On Developments set 'Decision / Escalation Required? = Yes' with the ask, decision owner and date.
5 · Weekly Status Log | Add a row with the meeting date. The Weekly Report switches to that week automatically.
6 · Weekly Report | Review sections 1–8. Compare the indicator-based status with your call; resolve any CHALLENGE flag. Then write your RAG, one-sentence 'Why' and commentary in the Weekly Status Log row.
7 · Present | Print or export the Weekly Report tab to PDF (landscape, fits to width). After the meeting, record decisions and actions in the same log row and create the tasks.
WEEKLY REPORT SECTIONS
1 · Overall timeline | Mission dates, % elapsed, current phase and a text Gantt of the phase plan (Mission Charter) with a today marker.
2 · Overall status | Your RAG and one-sentence rationale, previous week and trend, indicator-based RAG from 13 drivers with editable thresholds, and a 2LoD consistency check.
3 · Progress since last week | Tasks completed; tasks moved forward; KPI week-on-week movement; developments and decisions; meetings held.
4 · Current work | All tasks In Progress with % complete, due flag and latest note.
5 · Findings | Only findings discovered or materially changed in the period, with remediation owner, status, target date, SLA and RAF; plus remediation targets due by end of next week.
6 · Blockers / dependencies | Blocked tasks and tasks waiting on a named person/team; overdue or outstanding responses from 1LoD and third parties.
7 · Plan for next week | Open tasks flagged for next week, due by end of next week (incl. overdue) or starting next week.
8 · Escalation / decision needed | Open decisions and escalations (Developments) and open findings in RAF breach.
Reporting period | Defaults to the day after the previous log entry up to the meeting date (or the last 7 days). Both dates can be overridden in the white cells at the top of the Weekly Report.
LEGEND
White cell | Your input. Type, paste or pick from the dropdown.
Grey cell | Automatic formula (IDs, flags, days open, SLA, progress, report content). Do not overwrite.
Light-green cell | Key assumption (Severity → SLA table on Lists). Review and align to the bank's standard.
Red / amber / green | Conditional formatting: overdue, SLA breach, RAF breach, RAG, status and severity.
Example rows | Row 5 of every log tab is an illustrative example (italic), dated in the current week so the Weekly Report shows how it works. Overwrite or delete before go-live.
Hidden helper columns | Columns headed 'WR helper' (grey, grouped and collapsed at the right of each log) feed the Weekly Report. Do not delete them; expand with the [+] button if needed.
TABS
Weekly Report | Auto-built weekly status pack (sections 1–8).
Weekly Status Log (WSR-) | One row per weekly meeting: RAG, why, commentary per section, decisions and actions; previous RAG and trend calculate automatically.
Dashboard | Cumulative mission KPIs and charts, including latest reported vs indicator-based RAG.
Mission Charter | Scope, objectives, drivers, governance and the 6-phase plan driving the timeline.
Goals & KPIs (GOL-) | Objectives and key results with last-week vs current value and progress to target.
Meetings (MTG-) / Emails (EML-) | Meetings with decisions, 2LoD challenge and follow-ups; material emails with response SLAs.
Tasks (TSK-) | Actions with owner, priority, progress notes, dependencies and next-week flag.
Developments (DEV-) | Milestones, decisions, scope changes, escalations and risk acceptances, including decision asks and outcomes.
EASM Findings (FND-) | Exposure register: technical vector → operational vulnerability → systemic/concentration risk → financial/regulatory impact → RAF, with SLA and weekly change tracking.
Stakeholders (STK-) / Lists | RACI, stance and contact cadence; dropdown values and the SLA table.
Cross-referencing | Link records by ID (e.g. a task's Source Ref = MTG-004). Separate multiple IDs with ';'.

## Weekly Report
EASM Mission — Weekly Status Report
Reporting period: 14-Oct-2026 to 20-Oct-2026 ¦ Meeting date: 20-Oct-2026 ¦ Generated: 20-Oct-2026
| Meeting date — override (optional) |  |  | Period start | 2026-10-14 |  | How it works: add this week's row in 'Weekly Status Log' (date + RAG + one sentence). Everything below fills automatically from the logs for the period shown.
| Meeting date used | 2026-10-20 |  | Period end | 2026-10-20
| Previous meeting (from Weekly Status Log) |  |  | Next week from | 2026-10-21
| Period start — override (optional) |  |  | Next week to | 2026-10-27
| Weekly Status Log entry | WSR-001 | [5 empty] | 1
1 · OVERALL TIMELINE
| Mission start | 2026-10-01 |  | Planned end |  | 2027-03-31
| Days elapsed | 19 |  | Days remaining |  | 162
| % of timeline elapsed | 10.5% |  | Phases completed |  | 1 of 6
| Current phase | 2. Discovery & Attribution |  | Current phase ends |  | 2026-11-14
Phase | Phase name | Status | Planned start | Planned end | Actual end | Variance (d) | Timeline (█ planned · ▼ today)
| Scale: 01-Oct-26 → 31-Mar-27 | [5 empty] | ▼ 20-Oct
P1 | 1. Scoping & Baseline | Completed | 2026-10-01 | 2026-10-17 | 2026-10-16 | -1 | ████
P2 | 2. Discovery & Attribution | In Progress | 2026-10-12 | 2026-11-14 |  |  | ███████
P3 | 3. Exposure Assessment | Not Started | 2026-11-02 | 2026-12-19 |  |  | ██████████
P4 | 4. Risk Translation & 1LoD Challenge | Not Started | 2026-11-30 | 2027-01-29 |  |  | █████████████
P5 | 5. Remediation Oversight | Not Started | 2027-01-04 | 2027-03-12 |  |  | ███████████████
P6 | 6. Reporting & Closure | Not Started | 2027-03-01 | 2027-03-31 |  |  | ███████
2 · OVERALL STATUS
| Reported status (your call) | Amber | Discovery is on plan, but attribution is constrained by an outstanding 1LoD CMDB extract and an open sponsor decision on scope extension.
| Previous week / trend | —
| Indicator-based status (suggested) | Amber | 0 Red and 1 Amber driver(s) triggered — see table below
| 2LoD consistency check |  | Consistent with indicators
| Status driver (from logs) | Count | Drives | Threshold (≥) | Triggered | Source tab
| Open Critical/High findings breaching remediation SLA | 0 | Red | 1 | — | EASM Findings
| RAF appetite breaches (open findings + developments) | 0 | Red | 1 | — | Findings / Developments
| Goals Off Track | 0 | Red | 1 | — | Goals & KPIs
| Overdue Critical-priority tasks | 0 | Red | 1 | — | Tasks
| Mission past planned end with phases open | 0 | Red | 1 | — | Mission Charter
| Overdue tasks (all priorities) | 0 | Amber | 1 | — | Tasks
| Blocked tasks | 0 | Amber | 1 | — | Tasks
| Goals At Risk | 0 | Amber | 1 | — | Goals & KPIs
| Overdue responses from 1LoD / third parties | 0 | Amber | 1 | — | Emails
| Open decisions / escalations awaiting outcome | 1 | Amber | 1 | Amber | Developments
| Open Medium/Low findings breaching SLA | 0 | Amber | 1 | — | EASM Findings
| RAF tolerance breaches (open findings + developments) | 0 | Amber | 1 | — | Findings / Developments
| Phases delayed or finished late | 0 | Amber | 1 | — | Mission Charter
Thresholds (white cells) are editable — calibrate to the mission's risk tolerance. Any Red driver ⇒ Red; otherwise any Amber driver ⇒ Amber; otherwise Green.
3 · PROGRESS SINCE LAST WEEK
Tasks completed in the period | [6 empty] | Showing 0 of 0
ID | Task | Workstream | Owner | Status | Completed | Due | Evidence of closure
— None —
Tasks moved forward (updated in the period, still open) | [6 empty] | Showing 1 of 1
ID | Task | Workstream | Owner | Status | Updated | Due | % complete · progress note
TSK-001 | Reconcile EASM-discovered assets against CMDB extract; quantify unattributed / unknown assets by legal entity | Attribution & Ownership | Me (2LoD CRI) | In Progress | 2026-10-19 | 2026-11-06 | 25% · CMDB extract received for 2 of 3 entities; reconciliation of Entity A complete (41 unmapped hosts) | 5
Goals & KPIs — week-on-week movement | [6 empty] | Showing 1 of 1
ID | Key result / KPI | Last week → now | Change | Status | Updated | Progress | Commentary
GOL-001 | % of discovered internet-facing assets attributed to an accountable owner | 66 → 70 % | +4.0 WoW | On Track | 2026-10-19 | 24.24% | Uplift from Entity A reconciliation; Entity C extract outstanding (TSK-001) | 5
Developments, milestones & decisions recorded | [6 empty] | Showing 1 of 1
ID | Development | Type | Impact | RAF alignment | Date | Linked IDs | Assessment
DEV-001 | EASM scope extension to 3 acquired entities | Scope Change | High | Not Assessed | 2026-10-15 | MTG-001; TSK-001 | Acquired estates likely run legacy remote-access stacks outside Group patch governance – elevated concentration of unmanaged exposure | 5
Meetings held | [6 empty] | Showing 1 of 1
ID | Meeting | Type | Organiser | LoD | Date | Follow-up | Decisions taken
MTG-001 | EASM baseline – scope validation with Group Infrastructure | Working Session | Me (2LoD CRI) | Multiple | 2026-10-15 | 2026-10-30 | Scope extension to 3 acquired entities proposed to Mission Sponsor (DEV-001) | 5
Comment | Phase 1 closed; Entity A reconciled (+4pp attribution); critical legacy VPN exposure identified at acquired Entity B.
4 · CURRENT WORK
Tasks In Progress | [6 empty] | Showing 1 of 1
ID | Task | Workstream | Owner | Priority | Start | Due | % complete · due flag · latest note
TSK-001 | Reconcile EASM-discovered assets against CMDB extract; quantify unattributed / unknown assets by legal entity | Attribution & Ownership | Me (2LoD CRI) | High | 2026-10-16 | 2026-11-06 | 25% · On Schedule · CMDB extract received for 2 of 3 entities; reconciliation of Entity A complete (41 unmapped hosts) | 5
Comment | CMDB reconciliation for Entities B–C; validation of FND-001 with Network Security.
5 · FINDINGS — NEW OR MATERIALLY CHANGED
New in period: 1 ¦ Materially changed: 0 ¦ Open (total): 1 ¦ Open Critical/High: 1 ¦ SLA breaches: 0 ¦ Actively exploited (open): 0
New / changed findings and remediation status | [6 empty] | Showing 1 of 1
ID | Asset — exposure | Severity | Remediation owner | Remediation status | Discovered | Target date | New / change · SLA · RAF
FND-001 | legacy-vpn.acquired-entity.example — Legacy SSL VPN appliance exposed to internet with outdated firmware | Critical | Network Security (1LoD) | Validating | 2026-10-16 | 2026-10-31 | NEW — Severity raised High → Critical after vendor advisory ¦ SLA: Within SLA ¦ RAF: Not Assessed | 5
Remediation targets due by end of next week (incl. overdue) | [6 empty] | Showing 0 of 0
ID | Asset — exposure | Severity | Remediation owner | Status | Discovered | Target date | SLA flag
— None —
Comment | FND-001 (Critical) under validation; single-vendor remote-access concentration across acquired entities.
6 · BLOCKERS / DEPENDENCIES
Blocked tasks and dependencies on others | [6 empty] | Showing 1 of 1
ID | Task | Workstream | Dependency on | Status | Needed by | Task due | Blocker / dependency detail
TSK-001 | Reconcile EASM-discovered assets against CMDB extract; quantify unattributed / unknown assets by legal entity | Attribution & Ownership | Network Security (1LoD) | In Progress | 2026-10-23 | 2026-11-06 | CMDB extract for acquired Entity C outstanding (EML-001) | 5
Responses awaited (1LoD / third parties) | [6 empty] | Showing 1 of 1
ID | Subject | Category | Counterparty | Response status | Sent | Response due | Flag — ask
EML-001 | RFI – CMDB extract of internet-facing assets | Request for Information | Head of Network Security; cc CISO Office | Awaiting Response | 2026-10-16 | 2026-10-23 | Open — Full extract incl. owner, legal entity, hosting and last patch date | 5
Comment | Entity C CMDB extract (Network Security, needed 23-Oct).
7 · PLAN FOR NEXT WEEK
Planned tasks | [6 empty] | Showing 1 of 1
Open tasks flagged 'Planned for Next Week? = Yes', due by end of next week (incl. overdue), or starting next week.
ID | Task | Workstream | Owner | Priority | Start | Due | Status · due flag
TSK-001 | Reconcile EASM-discovered assets against CMDB extract; quantify unattributed / unknown assets by legal entity | Attribution & Ownership | Me (2LoD CRI) | High | 2026-10-16 | 2026-11-06 | In Progress · On Schedule | 5
Comment | Complete reconciliation; confirm FND-001 exploitability and remediation owner; prepare Phase 3 test plan.
8 · ESCALATION / DECISION NEEDED
Open decisions and escalations | [6 empty] | Showing 1 of 1
ID | Decision / ask | Type | Needed from | Decision status | Raised | Needed by | Impact · risk dimension · RAF
DEV-001 | Approve extension of EASM scope to 3 acquired entities and +3 weeks on Phase 2 | Scope Change | Mission Sponsor | Open | 2026-10-15 | 2026-10-30 | High impact · Systemic / Concentration · RAF: Not Assessed | 5
Open findings in RAF breach (escalation candidates) | [6 empty] | Showing 0 of 0
ID | Asset — exposure | Severity | Remediation owner | Status | Discovered | Target date | RAF alignment — financial / regulatory impact
— None —
Comment | Sponsor approval of scope extension and +3 weeks on Phase 2 (DEV-001, by 30-Oct).
End of report. Lists are capped; 'Showing x of y' turns red when items are cut — see the source tab for the full list.

## Weekly Status Log
Weekly Status Log
One row per weekly meeting: your RAG call, one-sentence rationale and commentary. The Weekly Report picks up the latest row automatically.
White cells = your input ¦ Grey cells = automatic (do not overwrite) ¦ Row 5 is an illustrative example (italic) — overwrite or delete it.
Week ID | Meeting Date | Overall Status (RAG) | Why — one sentence | Progress Highlights (commentary) | Current Work (commentary) | Findings Commentary | Blockers / Dependencies (commentary) | Plan for Next Week (commentary) | Escalation / Decision Needed (commentary) | Decisions Taken at Meeting | Actions Agreed (Task IDs) | Previous RAG | RAG Trend | Notes
WSR-001 | 2026-10-20 | Amber | Discovery is on plan, but attribution is constrained by an outstanding 1LoD CMDB extract and an open sponsor decision on scope extension. | Phase 1 closed; Entity A reconciled (+4pp attribution); critical legacy VPN exposure identified at acquired Entity B. | CMDB reconciliation for Entities B–C; validation of FND-001 with Network Security. | FND-001 (Critical) under validation; single-vendor remote-access concentration across acquired entities. | Entity C CMDB extract (Network Security, needed 23-Oct). | Complete reconciliation; confirm FND-001 exploitability and remediation owner; prepare Phase 3 test plan. | Sponsor approval of scope extension and +3 weeks on Phase 2 (DEV-001, by 30-Oct).
WSR-002
WSR-003
WSR-004
WSR-005
WSR-006
WSR-007
WSR-008
WSR-009
WSR-010
WSR-011
WSR-012
WSR-013
WSR-014
WSR-015
WSR-016
WSR-017
WSR-018
WSR-019
WSR-020
WSR-021
WSR-022
WSR-023
WSR-024
WSR-025
WSR-026
WSR-027
WSR-028
WSR-029
WSR-030
WSR-031
WSR-032
WSR-033
WSR-034
WSR-035
WSR-036
WSR-037
WSR-038
WSR-039
WSR-040
WSR-041
WSR-042
WSR-043
WSR-044
WSR-045
WSR-046
WSR-047
WSR-048
WSR-049
WSR-050
WSR-051
WSR-052
WSR-053
WSR-054
WSR-055
WSR-056
WSR-057
WSR-058
WSR-059
WSR-060
WSR-061
WSR-062
WSR-063
WSR-064
WSR-065
WSR-066
WSR-067
WSR-068
WSR-069
WSR-070
WSR-071
WSR-072
WSR-073
WSR-074
WSR-075
WSR-076
WSR-077
WSR-078
WSR-079
WSR-080
WSR-081
WSR-082
WSR-083
WSR-084
WSR-085
WSR-086
WSR-087
WSR-088
WSR-089
WSR-090
WSR-091
WSR-092
WSR-093
WSR-094
WSR-095
WSR-096
WSR-097
WSR-098
WSR-099
WSR-100
WSR-101
WSR-102
WSR-103
WSR-104
Note on B4: One row per weekly meeting. The Weekly Report automatically uses the latest date entered here.

## Dashboard
EASM Mission Dashboard
As of | 2026-10-20 | All figures calculate automatically from the log tabs. Do not type here.
Weekly Status |  | Tasks by Status | Count
Reported RAG (latest weekly meeting) | Amber | Not Started | 0
Indicator-based RAG | Amber | In Progress | 1
Trend vs previous week |  | Blocked | 0
|  | On Hold | 0
Mission Timeline |  | Completed | 0
Days elapsed | 19 | Cancelled | 0
Days remaining | 162
% of timeline elapsed | 10.5% | Findings by Severity | Count | Open
|  | Critical | 1 | 1
Meetings |  | High | 0 | 0
Meetings logged | 1 | Medium | 0 | 0
Meetings in last 30 days | 1 | Low | 0 | 0
Overdue follow-ups | 0 | Informational | 0 | 0
Emails & Communications |  | Findings by Status | Count
Emails logged | 1 | New | 0
Awaiting response | 1 | Validating | 1
Overdue responses | 0 | Confirmed | 0
Average days to respond | - | Remediation In Progress | 0
Escalations | 0 | Remediated | 0
|  | Risk Accepted | 0
Tasks |  | False Positive | 0
Tasks logged | 1
Open tasks | 1 | Goals by Status | Count
Overdue tasks | 0 | On Track | 1
Due within 7 days | 0 | At Risk | 0
Blocked tasks | 0 | Off Track | 0
Completion rate (excl. cancelled) | 0% | Achieved | 0
|  | Deferred | 0
Goals & KPIs
Goals defined | 1 | Meetings by Type | Count
Average progress to target | 24.24% | Weekly Status Meeting | 0
Goals At Risk / Off Track | 0 | Kick-off | 0
Goals achieved | 0 | Steering Committee | 0
|  | Working Session | 1
EASM Findings |  | 1LoD Challenge Session | 0
Findings logged | 1 | Stakeholder Interview | 0
Open findings | 1 | Vendor / Tooling | 0
Open Critical / High | 1 | Risk Committee / Forum | 0
Open & actively exploited (KEV/TI) | 0 | Ad-hoc | 0
SLA breaches (open) | 0
Assets not in inventory (shadow IT) | 1 | Open Tasks by Priority | Count
Unknown-asset ratio | 100% | Critical | 0
Risk acceptances | 0 | High | 1
Average days open (all findings) | 4 | Medium | 0
|  | Low | 0
Developments & RAF
Developments logged | 1
Open decisions / escalations | 1
Items for committee reporting | 1
RAF breaches (findings + developments) | 0

## Mission Charter
EASM Mission Charter
Fill once at mission start; update when scope, timeline or governance changes. The phase plan drives the Weekly Report timeline.
Mission name | External Attack Surface Management (EASM) – 2LoD Assessment
Mission reference
Mission sponsor
Mission lead (2LoD CRI)
Start date | 2026-10-01
Planned end date | 2027-03-31
Days elapsed | 19
Days remaining | 162
% of timeline elapsed | 10.5%
Mission objective
In scope (entities, domains, IP ranges, cloud tenants)
Out of scope
Regulatory / supervisory drivers | e.g. DORA ICT asset identification, supervisory expectations, internal audit points
RAF metrics / KRIs linked
EASM tooling & data sources
1LoD counterparts
Governance forum & weekly meeting cadence
Key assumptions
Constraints / limitations
Success criteria
Phase Plan
Phase | Description | Planned Start | Planned End | Actual End | Status | Variance (days)
1. Scoping & Baseline | Confirm entities, seeds (domains, ASNs, IP ranges, cloud tenants) and tooling | 2026-10-01 | 2026-10-17 | 2026-10-16 | Completed | -1
2. Discovery & Attribution | Run discovery; attribute assets to owners and legal entities; reconcile vs CMDB | 2026-10-12 | 2026-11-14 |  | In Progress
3. Exposure Assessment | Identify exposed services, vulnerabilities, misconfigurations, leaked credentials | 2026-11-02 | 2026-12-19 |  | Not Started
4. Risk Translation & 1LoD Challenge | Translate exposures into operational, systemic, financial and RAF impact; challenge 1LoD premises | 2026-11-30 | 2027-01-29 |  | Not Started
5. Remediation Oversight | Track remediation against SLAs; review risk acceptances | 2027-01-04 | 2027-03-12 |  | Not Started
6. Reporting & Closure | Committee reporting, lessons learned, transition to BAU monitoring | 2027-03-01 | 2027-03-31 |  | Not Started
Phase dates in italic are illustrative — replace with your plan.

## Goals & KPIs
Goals & KPIs
Mission objectives and measurable key results — week-on-week movement and automatic progress.
White cells = your input ¦ Grey cells = automatic (do not overwrite) ¦ Row 5 is an illustrative example (italic) — overwrite or delete it.
Goal ID | Goal / Objective | Workstream | Key Result / KPI | Metric Definition | Unit | Baseline | Target | Value Last Week | Current Value | Δ vs Last Week | Progress to Target | Owner | Target Date | Days to Target | Status | RAF Linkage (KRI / Limit) | Last Updated | Commentary | WR helper: updated
GOL-001 | Establish a complete, attributed inventory of internet-facing assets | Attribution & Ownership | % of discovered internet-facing assets attributed to an accountable owner | Attributed assets ÷ total discovered assets (EASM platform, weekly snapshot) | % | 62 | 95 | 66 | 70 | 4 | 24.24% | Me (2LoD CRI) | 2026-12-31 | 72 | On Track | Cyber RAF – ICT asset management KRI | 2026-10-19 | Uplift from Entity A reconciliation; Entity C extract outstanding (TSK-001) | 5
GOL-002
GOL-003
GOL-004
GOL-005
GOL-006
GOL-007
GOL-008
GOL-009
GOL-010
GOL-011
GOL-012
GOL-013
GOL-014
GOL-015
GOL-016
GOL-017
GOL-018
GOL-019
GOL-020
GOL-021
GOL-022
GOL-023
GOL-024
GOL-025
GOL-026
GOL-027
GOL-028
GOL-029
GOL-030
GOL-031
GOL-032
GOL-033
GOL-034
GOL-035
GOL-036
GOL-037
GOL-038
GOL-039
GOL-040
GOL-041
GOL-042
GOL-043
GOL-044
GOL-045
GOL-046
GOL-047
GOL-048
GOL-049
GOL-050
GOL-051
GOL-052
GOL-053
GOL-054
GOL-055
GOL-056
GOL-057
GOL-058
GOL-059
GOL-060
GOL-061
GOL-062
GOL-063
GOL-064
GOL-065
GOL-066
GOL-067
GOL-068
GOL-069
GOL-070
GOL-071
GOL-072
GOL-073
GOL-074
GOL-075
GOL-076
GOL-077
GOL-078
GOL-079
GOL-080
GOL-081
GOL-082
GOL-083
GOL-084
GOL-085
GOL-086
GOL-087
GOL-088
GOL-089
GOL-090
GOL-091
GOL-092
GOL-093
GOL-094
GOL-095
GOL-096
GOL-097
GOL-098
GOL-099
GOL-100
GOL-101
GOL-102
GOL-103
GOL-104
GOL-105
GOL-106
GOL-107
GOL-108
GOL-109
GOL-110
GOL-111
GOL-112
GOL-113
GOL-114
GOL-115
GOL-116
GOL-117
GOL-118
GOL-119
GOL-120
GOL-121
GOL-122
GOL-123
GOL-124
GOL-125
GOL-126
GOL-127
GOL-128
GOL-129
GOL-130
GOL-131
GOL-132
GOL-133
GOL-134
GOL-135
GOL-136
GOL-137
GOL-138
GOL-139
GOL-140
GOL-141
GOL-142
GOL-143
GOL-144
GOL-145
GOL-146
GOL-147
GOL-148
GOL-149
GOL-150
GOL-151
GOL-152
GOL-153
GOL-154
GOL-155
GOL-156
GOL-157
GOL-158
GOL-159
GOL-160
GOL-161
GOL-162
GOL-163
GOL-164
GOL-165
GOL-166
GOL-167
GOL-168
GOL-169
GOL-170
GOL-171
GOL-172
GOL-173
GOL-174
GOL-175
GOL-176
GOL-177
GOL-178
GOL-179
GOL-180
GOL-181
GOL-182
GOL-183
GOL-184
GOL-185
GOL-186
GOL-187
GOL-188
GOL-189
GOL-190
GOL-191
GOL-192
GOL-193
GOL-194
GOL-195
GOL-196
GOL-197
GOL-198
GOL-199
GOL-200
GOL-201
GOL-202
GOL-203
GOL-204
GOL-205
GOL-206
GOL-207
GOL-208
GOL-209
GOL-210
GOL-211
GOL-212
GOL-213
GOL-214
GOL-215
GOL-216
GOL-217
GOL-218
GOL-219
GOL-220
GOL-221
GOL-222
GOL-223
GOL-224
GOL-225
GOL-226
GOL-227
GOL-228
GOL-229
GOL-230
GOL-231
GOL-232
GOL-233
GOL-234
GOL-235
GOL-236
GOL-237
GOL-238
GOL-239
GOL-240
GOL-241
GOL-242
GOL-243
GOL-244
GOL-245
GOL-246
GOL-247
GOL-248
GOL-249
GOL-250
GOL-251
GOL-252
GOL-253
GOL-254
GOL-255
GOL-256
GOL-257
GOL-258
GOL-259
GOL-260
GOL-261
GOL-262
GOL-263
GOL-264
GOL-265
GOL-266
GOL-267
GOL-268
GOL-269
GOL-270
GOL-271
GOL-272
GOL-273
GOL-274
GOL-275
GOL-276
GOL-277
GOL-278
GOL-279
GOL-280
GOL-281
GOL-282
GOL-283
GOL-284
GOL-285
GOL-286
GOL-287
GOL-288
GOL-289
GOL-290
GOL-291
GOL-292
GOL-293
GOL-294
GOL-295
GOL-296
GOL-297
GOL-298
GOL-299
GOL-300
Formulas:
Days to Target = IF([Target Date]="","",[Target Date]-TODAY())
Note on I4: Copy the previous 'Current Value' here before updating it each week.
Note on L4: (Current − Baseline) / (Target − Baseline), capped 0–100%. Works for 'higher is better' and 'lower is better' KPIs.
Note on R4: Feeds 'Progress since last week' when it falls in the reporting period.

## Meetings
Meetings Log
Every meeting held under the EASM mission: participants, decisions, 2LoD challenge and follow-ups.
White cells = your input ¦ Grey cells = automatic (do not overwrite) ¦ Row 5 is an illustrative example (italic) — overwrite or delete it.
Meeting ID | Date | Start Time | Duration (min) | Meeting Type | Workstream | Title / Subject | Organiser | Attendees (name – function) | LoD Represented | Agenda / Purpose | Key Discussion Points | Decisions Taken | 2LoD Challenge Raised | 1LoD Position / Response | Actions Generated (Task IDs) | Follow-up Required? | Follow-up Date | Follow-up Completed? | Follow-up Flag | Minutes / Recording Link | Classification | Notes | WR helper: held in period
MTG-001 | 2026-10-15 | 10:00 | 60 | Working Session | Asset Discovery | EASM baseline – scope validation with Group Infrastructure | Me (2LoD CRI) | Head of Network Security; CISO Office; Group Architecture | Multiple | Validate in-scope legal entities, IP ranges and root domains for EASM baseline | EASM platform shows ~18% of discovered hosts not mapped in CMDB; 3 recently acquired entities not onboarded | Scope extension to 3 acquired entities proposed to Mission Sponsor (DEV-001) | 1LoD claim of 95% inventory completeness not evidenced; reconciliation requested | 1LoD to provide CMDB extract of internet-facing assets | TSK-001 | Yes | 2026-10-30 | No | Scheduled | SharePoint/EASM/Minutes/MTG-001 | Confidential |  | 5
MTG-002
MTG-003
MTG-004
MTG-005
MTG-006
MTG-007
MTG-008
MTG-009
MTG-010
MTG-011
MTG-012
MTG-013
MTG-014
MTG-015
MTG-016
MTG-017
MTG-018
MTG-019
MTG-020
MTG-021
MTG-022
MTG-023
MTG-024
MTG-025
MTG-026
MTG-027
MTG-028
MTG-029
MTG-030
MTG-031
MTG-032
MTG-033
MTG-034
MTG-035
MTG-036
MTG-037
MTG-038
MTG-039
MTG-040
MTG-041
MTG-042
MTG-043
MTG-044
MTG-045
MTG-046
MTG-047
MTG-048
MTG-049
MTG-050
MTG-051
MTG-052
MTG-053
MTG-054
MTG-055
MTG-056
MTG-057
MTG-058
MTG-059
MTG-060
MTG-061
MTG-062
MTG-063
MTG-064
MTG-065
MTG-066
MTG-067
MTG-068
MTG-069
MTG-070
MTG-071
MTG-072
MTG-073
MTG-074
MTG-075
MTG-076
MTG-077
MTG-078
MTG-079
MTG-080
MTG-081
MTG-082
MTG-083
MTG-084
MTG-085
MTG-086
MTG-087
MTG-088
MTG-089
MTG-090
MTG-091
MTG-092
MTG-093
MTG-094
MTG-095
MTG-096
MTG-097
MTG-098
MTG-099
MTG-100
MTG-101
MTG-102
MTG-103
MTG-104
MTG-105
MTG-106
MTG-107
MTG-108
MTG-109
MTG-110
MTG-111
MTG-112
MTG-113
MTG-114
MTG-115
MTG-116
MTG-117
MTG-118
MTG-119
MTG-120
MTG-121
MTG-122
MTG-123
MTG-124
MTG-125
MTG-126
MTG-127
MTG-128
MTG-129
MTG-130
MTG-131
MTG-132
MTG-133
MTG-134
MTG-135
MTG-136
MTG-137
MTG-138
MTG-139
MTG-140
MTG-141
MTG-142
MTG-143
MTG-144
MTG-145
MTG-146
MTG-147
MTG-148
MTG-149
MTG-150
MTG-151
MTG-152
MTG-153
MTG-154
MTG-155
MTG-156
MTG-157
MTG-158
MTG-159
MTG-160
MTG-161
MTG-162
MTG-163
MTG-164
MTG-165
MTG-166
MTG-167
MTG-168
MTG-169
MTG-170
MTG-171
MTG-172
MTG-173
MTG-174
MTG-175
MTG-176
MTG-177
MTG-178
MTG-179
MTG-180
MTG-181
MTG-182
MTG-183
MTG-184
MTG-185
MTG-186
MTG-187
MTG-188
MTG-189
MTG-190
MTG-191
MTG-192
MTG-193
MTG-194
MTG-195
MTG-196
MTG-197
MTG-198
MTG-199
MTG-200
MTG-201
MTG-202
MTG-203
MTG-204
MTG-205
MTG-206
MTG-207
MTG-208
MTG-209
MTG-210
MTG-211
MTG-212
MTG-213
MTG-214
MTG-215
MTG-216
MTG-217
MTG-218
MTG-219
MTG-220
MTG-221
MTG-222
MTG-223
MTG-224
MTG-225
MTG-226
MTG-227
MTG-228
MTG-229
MTG-230
MTG-231
MTG-232
MTG-233
MTG-234
MTG-235
MTG-236
MTG-237
MTG-238
MTG-239
MTG-240
MTG-241
MTG-242
MTG-243
MTG-244
MTG-245
MTG-246
MTG-247
MTG-248
MTG-249
MTG-250
MTG-251
MTG-252
MTG-253
MTG-254
MTG-255
MTG-256
MTG-257
MTG-258
MTG-259
MTG-260
MTG-261
MTG-262
MTG-263
MTG-264
MTG-265
MTG-266
MTG-267
MTG-268
MTG-269
MTG-270
MTG-271
MTG-272
MTG-273
MTG-274
MTG-275
MTG-276
MTG-277
MTG-278
MTG-279
MTG-280
MTG-281
MTG-282
MTG-283
MTG-284
MTG-285
MTG-286
MTG-287
MTG-288
MTG-289
MTG-290
MTG-291
MTG-292
MTG-293
MTG-294
MTG-295
MTG-296
MTG-297
MTG-298
MTG-299
MTG-300
Formulas:
Follow-up Flag = IF([Follow-up Required?]<>"Yes","",IF([Follow-up Completed?]="Yes","Done",IF([Follow-up Date]="","Date missing",IF([Follow-up Date]<TODAY(),"OVERDUE","Scheduled"))))
Note on N4: Premises or evidence from 1LoD that were challenged in the meeting.

## Emails
Email & Communications Log
Material emails sent/received: requests, evidence, escalations and response SLAs.
White cells = your input ¦ Grey cells = automatic (do not overwrite) ¦ Row 5 is an illustrative example (italic) — overwrite or delete it.
Email ID | Date Sent / Received | Direction | From | To / Cc | Counterparty LoD | Subject | Category | Workstream | Summary | Request / Ask | Attachments / Evidence | Response Required? | Response Due | Response Status | Date Responded | Days to Respond | Response Flag | Linked IDs (MTG/TSK/FND) | Mail Reference / Link | Notes | WR helper: response awaited
EML-001 | 2026-10-16 | Outbound | Me (2LoD CRI) | Head of Network Security; cc CISO Office | 1LoD | RFI – CMDB extract of internet-facing assets | Request for Information | Attribution & Ownership | Formal request following MTG-001 for the CMDB extract to reconcile against EASM discovery output | Full extract incl. owner, legal entity, hosting and last patch date | None | Yes | 2026-10-23 | Awaiting Response |  |  | Open | MTG-001; TSK-001 | Outlook – EASM folder |  | 5
EML-002
EML-003
EML-004
EML-005
EML-006
EML-007
EML-008
EML-009
EML-010
EML-011
EML-012
EML-013
EML-014
EML-015
EML-016
EML-017
EML-018
EML-019
EML-020
EML-021
EML-022
EML-023
EML-024
EML-025
EML-026
EML-027
EML-028
EML-029
EML-030
EML-031
EML-032
EML-033
EML-034
EML-035
EML-036
EML-037
EML-038
EML-039
EML-040
EML-041
EML-042
EML-043
EML-044
EML-045
EML-046
EML-047
EML-048
EML-049
EML-050
EML-051
EML-052
EML-053
EML-054
EML-055
EML-056
EML-057
EML-058
EML-059
EML-060
EML-061
EML-062
EML-063
EML-064
EML-065
EML-066
EML-067
EML-068
EML-069
EML-070
EML-071
EML-072
EML-073
EML-074
EML-075
EML-076
EML-077
EML-078
EML-079
EML-080
EML-081
EML-082
EML-083
EML-084
EML-085
EML-086
EML-087
EML-088
EML-089
EML-090
EML-091
EML-092
EML-093
EML-094
EML-095
EML-096
EML-097
EML-098
EML-099
EML-100
EML-101
EML-102
EML-103
EML-104
EML-105
EML-106
EML-107
EML-108
EML-109
EML-110
EML-111
EML-112
EML-113
EML-114
EML-115
EML-116
EML-117
EML-118
EML-119
EML-120
EML-121
EML-122
EML-123
EML-124
EML-125
EML-126
EML-127
EML-128
EML-129
EML-130
EML-131
EML-132
EML-133
EML-134
EML-135
EML-136
EML-137
EML-138
EML-139
EML-140
EML-141
EML-142
EML-143
EML-144
EML-145
EML-146
EML-147
EML-148
EML-149
EML-150
EML-151
EML-152
EML-153
EML-154
EML-155
EML-156
EML-157
EML-158
EML-159
EML-160
EML-161
EML-162
EML-163
EML-164
EML-165
EML-166
EML-167
EML-168
EML-169
EML-170
EML-171
EML-172
EML-173
EML-174
EML-175
EML-176
EML-177
EML-178
EML-179
EML-180
EML-181
EML-182
EML-183
EML-184
EML-185
EML-186
EML-187
EML-188
EML-189
EML-190
EML-191
EML-192
EML-193
EML-194
EML-195
EML-196
EML-197
EML-198
EML-199
EML-200
EML-201
EML-202
EML-203
EML-204
EML-205
EML-206
EML-207
EML-208
EML-209
EML-210
EML-211
EML-212
EML-213
EML-214
EML-215
EML-216
EML-217
EML-218
EML-219
EML-220
EML-221
EML-222
EML-223
EML-224
EML-225
EML-226
EML-227
EML-228
EML-229
EML-230
EML-231
EML-232
EML-233
EML-234
EML-235
EML-236
EML-237
EML-238
EML-239
EML-240
EML-241
EML-242
EML-243
EML-244
EML-245
EML-246
EML-247
EML-248
EML-249
EML-250
EML-251
EML-252
EML-253
EML-254
EML-255
EML-256
EML-257
EML-258
EML-259
EML-260
EML-261
EML-262
EML-263
EML-264
EML-265
EML-266
EML-267
EML-268
EML-269
EML-270
EML-271
EML-272
EML-273
EML-274
EML-275
EML-276
EML-277
EML-278
EML-279
EML-280
EML-281
EML-282
EML-283
EML-284
EML-285
EML-286
EML-287
EML-288
EML-289
EML-290
EML-291
EML-292
EML-293
EML-294
EML-295
EML-296
EML-297
EML-298
EML-299
EML-300
Formulas:
Response Flag = IF(OR([Response Required?]<>"Yes",[Date Responded]<>"",[Response Status]="Closed",[Response Status]="No Action Required"),"",IF([Response Due]="","Due date missing",IF([Response Due]<TODAY(),"OVERDUE",IF([Response Due]-TODAY()<=2,"Due ≤2d","Open"))))

## Tasks
Task & Action Tracker
All actions arising from meetings, emails, findings and goals — ownership, progress notes, dependencies and next-week planning.
White cells = your input ¦ Grey cells = automatic (do not overwrite) ¦ Row 5 is an illustrative example (italic) — overwrite or delete it.
Task ID | Date Raised | Source | Source Ref ID | Workstream | Task Description | Linked Goal ID | Owner | Owner LoD | Priority | Status | Start Date | Due Date | Completion Date | % Complete | Planned for Next Week? | Last Update Date | Latest Update / Progress Note | Dependency On (Person / Team) | Needed By | Blocker / Dependency Detail | Evidence of Closure | Days Open | Due Flag | Notes | WR helper: completed | WR helper: moved forward | WR helper: current | WR helper: blocker | WR helper: next week
TSK-001 | 2026-10-15 | Meeting | MTG-001 | Attribution & Ownership | Reconcile EASM-discovered assets against CMDB extract; quantify unattributed / unknown assets by legal entity | GOL-001 | Me (2LoD CRI) | 2LoD | High | In Progress | 2026-10-16 | 2026-11-06 |  | 25% | Yes | 2026-10-19 | CMDB extract received for 2 of 3 entities; reconciliation of Entity A complete (41 unmapped hosts) | Network Security (1LoD) | 2026-10-23 | CMDB extract for acquired Entity C outstanding (EML-001) |  | 5 | On Schedule |  |  | 5 | 5 | 5 | 5
TSK-002
TSK-003
TSK-004
TSK-005
TSK-006
TSK-007
TSK-008
TSK-009
TSK-010
TSK-011
TSK-012
TSK-013
TSK-014
TSK-015
TSK-016
TSK-017
TSK-018
TSK-019
TSK-020
TSK-021
TSK-022
TSK-023
TSK-024
TSK-025
TSK-026
TSK-027
TSK-028
TSK-029
TSK-030
TSK-031
TSK-032
TSK-033
TSK-034
TSK-035
TSK-036
TSK-037
TSK-038
TSK-039
TSK-040
TSK-041
TSK-042
TSK-043
TSK-044
TSK-045
TSK-046
TSK-047
TSK-048
TSK-049
TSK-050
TSK-051
TSK-052
TSK-053
TSK-054
TSK-055
TSK-056
TSK-057
TSK-058
TSK-059
TSK-060
TSK-061
TSK-062
TSK-063
TSK-064
TSK-065
TSK-066
TSK-067
TSK-068
TSK-069
TSK-070
TSK-071
TSK-072
TSK-073
TSK-074
TSK-075
TSK-076
TSK-077
TSK-078
TSK-079
TSK-080
TSK-081
TSK-082
TSK-083
TSK-084
TSK-085
TSK-086
TSK-087
TSK-088
TSK-089
TSK-090
TSK-091
TSK-092
TSK-093
TSK-094
TSK-095
TSK-096
TSK-097
TSK-098
TSK-099
TSK-100
TSK-101
TSK-102
TSK-103
TSK-104
TSK-105
TSK-106
TSK-107
TSK-108
TSK-109
TSK-110
TSK-111
TSK-112
TSK-113
TSK-114
TSK-115
TSK-116
TSK-117
TSK-118
TSK-119
TSK-120
TSK-121
TSK-122
TSK-123
TSK-124
TSK-125
TSK-126
TSK-127
TSK-128
TSK-129
TSK-130
TSK-131
TSK-132
TSK-133
TSK-134
TSK-135
TSK-136
TSK-137
TSK-138
TSK-139
TSK-140
TSK-141
TSK-142
TSK-143
TSK-144
TSK-145
TSK-146
TSK-147
TSK-148
TSK-149
TSK-150
TSK-151
TSK-152
TSK-153
TSK-154
TSK-155
TSK-156
TSK-157
TSK-158
TSK-159
TSK-160
TSK-161
TSK-162
TSK-163
TSK-164
TSK-165
TSK-166
TSK-167
TSK-168
TSK-169
TSK-170
TSK-171
TSK-172
TSK-173
TSK-174
TSK-175
TSK-176
TSK-177
TSK-178
TSK-179
TSK-180
TSK-181
TSK-182
TSK-183
TSK-184
TSK-185
TSK-186
TSK-187
TSK-188
TSK-189
TSK-190
TSK-191
TSK-192
TSK-193
TSK-194
TSK-195
TSK-196
TSK-197
TSK-198
TSK-199
TSK-200
TSK-201
TSK-202
TSK-203
TSK-204
TSK-205
TSK-206
TSK-207
TSK-208
TSK-209
TSK-210
TSK-211
TSK-212
TSK-213
TSK-214
TSK-215
TSK-216
TSK-217
TSK-218
TSK-219
TSK-220
TSK-221
TSK-222
TSK-223
TSK-224
TSK-225
TSK-226
TSK-227
TSK-228
TSK-229
TSK-230
TSK-231
TSK-232
TSK-233
TSK-234
TSK-235
TSK-236
TSK-237
TSK-238
TSK-239
TSK-240
TSK-241
TSK-242
TSK-243
TSK-244
TSK-245
TSK-246
TSK-247
TSK-248
TSK-249
TSK-250
TSK-251
TSK-252
TSK-253
TSK-254
TSK-255
TSK-256
TSK-257
TSK-258
TSK-259
TSK-260
TSK-261
TSK-262
TSK-263
TSK-264
TSK-265
TSK-266
TSK-267
TSK-268
TSK-269
TSK-270
TSK-271
TSK-272
TSK-273
TSK-274
TSK-275
TSK-276
TSK-277
TSK-278
TSK-279
TSK-280
TSK-281
TSK-282
TSK-283
TSK-284
TSK-285
TSK-286
TSK-287
TSK-288
TSK-289
TSK-290
TSK-291
TSK-292
TSK-293
TSK-294
TSK-295
TSK-296
TSK-297
TSK-298
TSK-299
TSK-300
Formulas:
Days Open = IF([Date Raised]="","",IF([Completion Date]<>"",[Completion Date]-[Date Raised],TODAY()-[Date Raised]))
Due Flag = IF(OR([Due Date]="",[Status]="Completed",[Status]="Cancelled"),"",IF([Due Date]<TODAY(),"OVERDUE",IF([Due Date]-TODAY()<=7,"Due ≤7d","On Schedule")))
Note on N4: Feeds 'Progress since last week' when it falls in the reporting period.
Note on P4: Yes = appears in 'Plan for next week'. Open tasks due by end of next week appear automatically.
Note on Q4: Date of the latest material progress. Feeds 'Progress since last week'.
Note on S4: Who you are waiting on. Any value here puts the task in 'Blockers / dependencies'.

## Developments
Developments & Decisions Log
Milestones, decisions, scope changes, escalations and risk acceptances — facts, inferences and uncertainties kept separate.
White cells = your input ¦ Grey cells = automatic (do not overwrite) ¦ Row 5 is an illustrative example (italic) — overwrite or delete it.
Development ID | Date | Development Type | Workstream | Title | Description (Facts) | Inference / Assessment | Key Uncertainties | Source / Trigger | Impact Level | Primary Risk Dimension | RAF Alignment | Decision / Escalation Required? | Decision / Ask | Decision Needed From | Decision Needed By | Decision Status | Decision Outcome | Linked IDs | Committee Reporting? | Reported In (Forum / Date) | Notes | WR helper: in period | WR helper: open decision
DEV-001 | 2026-10-15 | Scope Change | Scoping & Governance | EASM scope extension to 3 acquired entities | Root domains and IP ranges of 3 entities acquired in 2025–26 were outside the original EASM baseline | Acquired estates likely run legacy remote-access stacks outside Group patch governance – elevated concentration of unmanaged exposure | Completeness of acquired-entity domain list; contractual hosting arrangements | MTG-001 | High | Systemic / Concentration | Not Assessed | Yes | Approve extension of EASM scope to 3 acquired entities and +3 weeks on Phase 2 | Mission Sponsor | 2026-10-30 | Open |  | MTG-001; TSK-001 | Yes | Cyber Risk Forum – Nov 2026 |  | 5 | 5
DEV-002
DEV-003
DEV-004
DEV-005
DEV-006
DEV-007
DEV-008
DEV-009
DEV-010
DEV-011
DEV-012
DEV-013
DEV-014
DEV-015
DEV-016
DEV-017
DEV-018
DEV-019
DEV-020
DEV-021
DEV-022
DEV-023
DEV-024
DEV-025
DEV-026
DEV-027
DEV-028
DEV-029
DEV-030
DEV-031
DEV-032
DEV-033
DEV-034
DEV-035
DEV-036
DEV-037
DEV-038
DEV-039
DEV-040
DEV-041
DEV-042
DEV-043
DEV-044
DEV-045
DEV-046
DEV-047
DEV-048
DEV-049
DEV-050
DEV-051
DEV-052
DEV-053
DEV-054
DEV-055
DEV-056
DEV-057
DEV-058
DEV-059
DEV-060
DEV-061
DEV-062
DEV-063
DEV-064
DEV-065
DEV-066
DEV-067
DEV-068
DEV-069
DEV-070
DEV-071
DEV-072
DEV-073
DEV-074
DEV-075
DEV-076
DEV-077
DEV-078
DEV-079
DEV-080
DEV-081
DEV-082
DEV-083
DEV-084
DEV-085
DEV-086
DEV-087
DEV-088
DEV-089
DEV-090
DEV-091
DEV-092
DEV-093
DEV-094
DEV-095
DEV-096
DEV-097
DEV-098
DEV-099
DEV-100
DEV-101
DEV-102
DEV-103
DEV-104
DEV-105
DEV-106
DEV-107
DEV-108
DEV-109
DEV-110
DEV-111
DEV-112
DEV-113
DEV-114
DEV-115
DEV-116
DEV-117
DEV-118
DEV-119
DEV-120
DEV-121
DEV-122
DEV-123
DEV-124
DEV-125
DEV-126
DEV-127
DEV-128
DEV-129
DEV-130
DEV-131
DEV-132
DEV-133
DEV-134
DEV-135
DEV-136
DEV-137
DEV-138
DEV-139
DEV-140
DEV-141
DEV-142
DEV-143
DEV-144
DEV-145
DEV-146
DEV-147
DEV-148
DEV-149
DEV-150
DEV-151
DEV-152
DEV-153
DEV-154
DEV-155
DEV-156
DEV-157
DEV-158
DEV-159
DEV-160
DEV-161
DEV-162
DEV-163
DEV-164
DEV-165
DEV-166
DEV-167
DEV-168
DEV-169
DEV-170
DEV-171
DEV-172
DEV-173
DEV-174
DEV-175
DEV-176
DEV-177
DEV-178
DEV-179
DEV-180
DEV-181
DEV-182
DEV-183
DEV-184
DEV-185
DEV-186
DEV-187
DEV-188
DEV-189
DEV-190
DEV-191
DEV-192
DEV-193
DEV-194
DEV-195
DEV-196
DEV-197
DEV-198
DEV-199
DEV-200
DEV-201
DEV-202
DEV-203
DEV-204
DEV-205
DEV-206
DEV-207
DEV-208
DEV-209
DEV-210
DEV-211
DEV-212
DEV-213
DEV-214
DEV-215
DEV-216
DEV-217
DEV-218
DEV-219
DEV-220
DEV-221
DEV-222
DEV-223
DEV-224
DEV-225
DEV-226
DEV-227
DEV-228
DEV-229
DEV-230
DEV-231
DEV-232
DEV-233
DEV-234
DEV-235
DEV-236
DEV-237
DEV-238
DEV-239
DEV-240
DEV-241
DEV-242
DEV-243
DEV-244
DEV-245
DEV-246
DEV-247
DEV-248
DEV-249
DEV-250
DEV-251
DEV-252
DEV-253
DEV-254
DEV-255
DEV-256
DEV-257
DEV-258
DEV-259
DEV-260
DEV-261
DEV-262
DEV-263
DEV-264
DEV-265
DEV-266
DEV-267
DEV-268
DEV-269
DEV-270
DEV-271
DEV-272
DEV-273
DEV-274
DEV-275
DEV-276
DEV-277
DEV-278
DEV-279
DEV-280
DEV-281
DEV-282
DEV-283
DEV-284
DEV-285
DEV-286
DEV-287
DEV-288
DEV-289
DEV-290
DEV-291
DEV-292
DEV-293
DEV-294
DEV-295
DEV-296
DEV-297
DEV-298
DEV-299
DEV-300
Note on M4: Yes + Decision Status Open = appears in 'Escalation / decision needed'.

## EASM Findings
EASM Findings Register
External attack surface exposures translated from technical vector to operational, systemic and RAF impact — with remediation SLA and weekly change tracking.
White cells = your input ¦ Grey cells = automatic (do not overwrite) ¦ Row 5 is an illustrative example (italic) — overwrite or delete it.
Finding ID | Date Discovered | Discovery Source | Asset Type | Asset Identifier (domain / IP / URL) | Attribution Confidence | Business Unit / Legal Entity | Asset Owner (1LoD) | In Asset Inventory? | Exposure (Technical Vector) | CVE / Weakness Ref | Severity | Actively Exploited? (KEV / TI) | Operational Vulnerability (2LoD View) | Systemic / Concentration Risk | Financial / Regulatory Impact | RAF Alignment | Remediation Owner | SLA (days) | Remediation Target Date | Status | Remediation / Closure Date | Last Material Change Date | Material Change Description | Weekly Report Tag | Days Open | SLA Flag | Linked Task ID | Risk Acceptance Ref | Notes | WR helper: new/changed | WR helper: remediation due | WR helper: RAF breach
FND-001 | 2026-10-16 | EASM Platform | Subdomain | legacy-vpn.acquired-entity.example | Medium | Retail Banking – Acquired Entity B | TBC | No | Legacy SSL VPN appliance exposed to internet with outdated firmware | To be confirmed | Critical | Unknown | Unmanaged remote-access entry point outside Group patch governance | Same VPN vendor used across several entities – single-vendor concentration in remote access | Potential major ICT incident classification and supervisory notification if exploited | Not Assessed | Network Security (1LoD) | 15 | 2026-10-31 | Validating |  | 2026-10-19 | Severity raised High → Critical after vendor advisory | NEW | 4 | Within SLA | TSK-001 |  |  | 5
FND-002
FND-003
FND-004
FND-005
FND-006
FND-007
FND-008
FND-009
FND-010
FND-011
FND-012
FND-013
FND-014
FND-015
FND-016
FND-017
FND-018
FND-019
FND-020
FND-021
FND-022
FND-023
FND-024
FND-025
FND-026
FND-027
FND-028
FND-029
FND-030
FND-031
FND-032
FND-033
FND-034
FND-035
FND-036
FND-037
FND-038
FND-039
FND-040
FND-041
FND-042
FND-043
FND-044
FND-045
FND-046
FND-047
FND-048
FND-049
FND-050
FND-051
FND-052
FND-053
FND-054
FND-055
FND-056
FND-057
FND-058
FND-059
FND-060
FND-061
FND-062
FND-063
FND-064
FND-065
FND-066
FND-067
FND-068
FND-069
FND-070
FND-071
FND-072
FND-073
FND-074
FND-075
FND-076
FND-077
FND-078
FND-079
FND-080
FND-081
FND-082
FND-083
FND-084
FND-085
FND-086
FND-087
FND-088
FND-089
FND-090
FND-091
FND-092
FND-093
FND-094
FND-095
FND-096
FND-097
FND-098
FND-099
FND-100
FND-101
FND-102
FND-103
FND-104
FND-105
FND-106
FND-107
FND-108
FND-109
FND-110
FND-111
FND-112
FND-113
FND-114
FND-115
FND-116
FND-117
FND-118
FND-119
FND-120
FND-121
FND-122
FND-123
FND-124
FND-125
FND-126
FND-127
FND-128
FND-129
FND-130
FND-131
FND-132
FND-133
FND-134
FND-135
FND-136
FND-137
FND-138
FND-139
FND-140
FND-141
FND-142
FND-143
FND-144
FND-145
FND-146
FND-147
FND-148
FND-149
FND-150
FND-151
FND-152
FND-153
FND-154
FND-155
FND-156
FND-157
FND-158
FND-159
FND-160
FND-161
FND-162
FND-163
FND-164
FND-165
FND-166
FND-167
FND-168
FND-169
FND-170
FND-171
FND-172
FND-173
FND-174
FND-175
FND-176
FND-177
FND-178
FND-179
FND-180
FND-181
FND-182
FND-183
FND-184
FND-185
FND-186
FND-187
FND-188
FND-189
FND-190
FND-191
FND-192
FND-193
FND-194
FND-195
FND-196
FND-197
FND-198
FND-199
FND-200
FND-201
FND-202
FND-203
FND-204
FND-205
FND-206
FND-207
FND-208
FND-209
FND-210
FND-211
FND-212
FND-213
FND-214
FND-215
FND-216
FND-217
FND-218
FND-219
FND-220
FND-221
FND-222
FND-223
FND-224
FND-225
FND-226
FND-227
FND-228
FND-229
FND-230
FND-231
FND-232
FND-233
FND-234
FND-235
FND-236
FND-237
FND-238
FND-239
FND-240
FND-241
FND-242
FND-243
FND-244
FND-245
FND-246
FND-247
FND-248
FND-249
FND-250
FND-251
FND-252
FND-253
FND-254
FND-255
FND-256
FND-257
FND-258
FND-259
FND-260
FND-261
FND-262
FND-263
FND-264
FND-265
FND-266
FND-267
FND-268
FND-269
FND-270
FND-271
FND-272
FND-273
FND-274
FND-275
FND-276
FND-277
FND-278
FND-279
FND-280
FND-281
FND-282
FND-283
FND-284
FND-285
FND-286
FND-287
FND-288
FND-289
FND-290
FND-291
FND-292
FND-293
FND-294
FND-295
FND-296
FND-297
FND-298
FND-299
FND-300
Formulas:
Remediation Target Date = IF(OR([SLA (days)]="",ISERROR([SLA (days)])),"",[Date Discovered]+[SLA (days)])
Days Open = IF([Date Discovered]="","",IF([Remediation / Closure Date]<>"",[Remediation / Closure Date]-[Date Discovered],TODAY()-[Date Discovered]))
SLA Flag = IF(OR([Date Discovered]="",[Remediation Target Date]="",[Status]="False Positive",[Status]="Risk Accepted"),"",IF([Remediation / Closure Date]<>"",IF([Remediation / Closure Date]>[Remediation Target Date],"Closed Late","Met"),IF(TODAY()>[Remediation Target Date],"SLA BREACH",IF([Remediation Target Date]-TODAY()<=7,"Due ≤7d","Within SLA"))))
Note on I4: 'No' = shadow / unmanaged asset. Drives the Dashboard 'unknown asset' ratio.
Note on S4: Looked up from the Severity → SLA table on the Lists tab (default values; align to your standard).
Note on W4: Set when severity, status, exploitation, RAF view or ownership changes materially. Feeds the weekly 'Findings' section.
Note on Y4: NEW = discovered in the Weekly Report period; CHANGED = material change recorded in the period.

## Stakeholders
Stakeholder Register
Who matters to the mission, their role, stance and contact cadence.
White cells = your input ¦ Grey cells = automatic (do not overwrite) ¦ Row 5 is an illustrative example (italic) — overwrite or delete it.
Stakeholder ID | Name | Role / Title | Function / Team | LoD | Legal Entity / Region | Email | Role in Mission (RACI) | Influence | Stance | Preferred Channel | Last Contact | Days Since Contact | Notes
STK-001 | [Name] | Head of Network Security | Group Infrastructure | 1LoD | Group / EU | name@bank.example | Responsible | High | Neutral | Meeting | 2026-10-15 | 5 | Owns remediation of perimeter assets; contests inventory gap
STK-002
STK-003
STK-004
STK-005
STK-006
STK-007
STK-008
STK-009
STK-010
STK-011
STK-012
STK-013
STK-014
STK-015
STK-016
STK-017
STK-018
STK-019
STK-020
STK-021
STK-022
STK-023
STK-024
STK-025
STK-026
STK-027
STK-028
STK-029
STK-030
STK-031
STK-032
STK-033
STK-034
STK-035
STK-036
STK-037
STK-038
STK-039
STK-040
STK-041
STK-042
STK-043
STK-044
STK-045
STK-046
STK-047
STK-048
STK-049
STK-050
STK-051
STK-052
STK-053
STK-054
STK-055
STK-056
STK-057
STK-058
STK-059
STK-060
STK-061
STK-062
STK-063
STK-064
STK-065
STK-066
STK-067
STK-068
STK-069
STK-070
STK-071
STK-072
STK-073
STK-074
STK-075
STK-076
STK-077
STK-078
STK-079
STK-080
STK-081
STK-082
STK-083
STK-084
STK-085
STK-086
STK-087
STK-088
STK-089
STK-090
STK-091
STK-092
STK-093
STK-094
STK-095
STK-096
STK-097
STK-098
STK-099
STK-100
STK-101
STK-102
STK-103
STK-104
STK-105
STK-106
STK-107
STK-108
STK-109
STK-110
STK-111
STK-112
STK-113
STK-114
STK-115
STK-116
STK-117
STK-118
STK-119
STK-120
STK-121
STK-122
STK-123
STK-124
STK-125
STK-126
STK-127
STK-128
STK-129
STK-130
STK-131
STK-132
STK-133
STK-134
STK-135
STK-136
STK-137
STK-138
STK-139
STK-140
STK-141
STK-142
STK-143
STK-144
STK-145
STK-146
STK-147
STK-148
STK-149
STK-150
STK-151
STK-152
STK-153
STK-154
STK-155
STK-156
STK-157
STK-158
STK-159
STK-160
STK-161
STK-162
STK-163
STK-164
STK-165
STK-166
STK-167
STK-168
STK-169
STK-170
STK-171
STK-172
STK-173
STK-174
STK-175
STK-176
STK-177
STK-178
STK-179
STK-180
STK-181
STK-182
STK-183
STK-184
STK-185
STK-186
STK-187
STK-188
STK-189
STK-190
STK-191
STK-192
STK-193
STK-194
STK-195
STK-196
STK-197
STK-198
STK-199
STK-200
STK-201
STK-202
STK-203
STK-204
STK-205
STK-206
STK-207
STK-208
STK-209
STK-210
STK-211
STK-212
STK-213
STK-214
STK-215
STK-216
STK-217
STK-218
STK-219
STK-220
STK-221
STK-222
STK-223
STK-224
STK-225
STK-226
STK-227
STK-228
STK-229
STK-230
STK-231
STK-232
STK-233
STK-234
STK-235
STK-236
STK-237
STK-238
STK-239
STK-240
STK-241
STK-242
STK-243
STK-244
STK-245
STK-246
STK-247
STK-248
STK-249
STK-250
STK-251
STK-252
STK-253
STK-254
STK-255
STK-256
STK-257
STK-258
STK-259
STK-260
STK-261
STK-262
STK-263
STK-264
STK-265
STK-266
STK-267
STK-268
STK-269
STK-270
STK-271
STK-272
STK-273
STK-274
STK-275
STK-276
STK-277
STK-278
STK-279
STK-280
STK-281
STK-282
STK-283
STK-284
STK-285
STK-286
STK-287
STK-288
STK-289
STK-290
STK-291
STK-292
STK-293
STK-294
STK-295
STK-296
STK-297
STK-298
STK-299
STK-300
Formulas:
Days Since Contact = IF([Last Contact]="","",TODAY()-[Last Contact])

## Lists
Dropdown lists — edit or extend values here (keep entries within the bordered block, 15 slots per list).
YesNo | YesNoUnknown | RAG | TaskStatus | Priority | MeetingType | Workstream | LoD | Direction | EmailCategory | ResponseStatus | TaskSource | GoalStatus | DevType | DecisionStatus | Impact | RiskDimension | RAF | AssetType | DiscoverySource | Confidence | FindingStatus | Confidentiality | RACI | Stance | Channel | PhaseStatus | Severity | Remediation SLA (days)
Yes | Yes | Green | Not Started | Critical | Weekly Status Meeting | Scoping & Governance | 1LoD | Inbound | Request for Information | Awaiting Response | Meeting | On Track | Milestone | Open | Critical | Operational | Within Appetite | Domain | EASM Platform | High | New | Internal | Responsible | Supportive | Email | Not Started | Critical | 15
No | No | Amber | In Progress | High | Kick-off | Asset Discovery | 2LoD | Outbound | Evidence Submission | Responded | Email | At Risk | Decision | Decided | High | Systemic / Concentration | Within Tolerance | Subdomain | Vulnerability Scanner | Medium | Validating | Confidential | Accountable | Neutral | Teams / Chat | In Progress | High | 30
| Unknown | Red | Blocked | Medium | Steering Committee | Attribution & Ownership | 3LoD |  | Status Update | Escalated | EASM Finding | Off Track | Key Finding | Deferred | Medium | Regulatory | Breach - Tolerance | IP Address / Range | Threat Intel Feed | Low | Confirmed | Strictly Confidential | Consulted | Resistant | Meeting | Completed | Medium | 90
|  |  | On Hold | Low | Working Session | Exposure Assessment | Third Party |  | Challenge / Pushback | Closed | Development | Achieved | Escalation | Withdrawn | Low | Financial | Breach - Appetite | Web Application | Certificate Transparency |  | Remediation In Progress |  | Informed | Unknown | Phone | Delayed | Low | 180
|  |  | Completed |  | 1LoD Challenge Session | Cloud Exposure | Multiple |  | Escalation | No Action Required | Goal | Deferred | Scope Change |  | Informational | Reputational | Not Assessed | API Endpoint | Passive DNS |  | Remediated |  |  |  | Formal Memo | On Hold | Informational | 365
|  |  | Cancelled |  | Stakeholder Interview | Shadow IT |  |  | Decision / Approval |  | Weekly Status Meeting |  | Risk Acceptance |  |  | Third-Party |  | Exposed Service / Port | Bug Bounty / Disclosure |  | Risk Accepted
[5 empty] | Vendor / Tooling | Third-Party / Supply Chain |  |  | Vendor Communication |  | Ad-hoc |  | Regulatory / Supervisory |  |  | Multiple |  | Cloud Resource | Manual OSINT |  | False Positive | [5 empty] | Key assumption: default SLA values for illustration only — align to the bank's Vulnerability Management Standard before use.
[5 empty] | Risk Committee / Forum | Brand & Domain Monitoring |  |  | FYI |  |  |  | Lesson Learned |  |  |  |  | TLS Certificate | 1LoD Disclosure
[5 empty] | Ad-hoc | Credential & Data Leakage | [11 empty] | Code Repository | Third-Party Notification
[6 empty] | Remediation Oversight | [11 empty] | Mobile App
[6 empty] | Reporting & RAF | [11 empty] | Email Infrastructure
Third-Party Hosted Asset